## Sheet1
ID | Activity | Responsible | Accountable | Consulted | Informed | Notes
1 | Open Search Setup | Accenture | Signet IT | Infoverity | N/A | Database setup for scaling enterprise data sources; ensure security compliance.
2 | S3 Data Buckets Setup | Accenture | Signet IT | Profound Analytics | Infoverity | Configure S3 buckets for strategic reporting; validate data ingestion pipeline.
3 | API Router Development | Accenture | Signet IT | Infoverity | Profound Analytics | Router to serve API for Prodevix; ensure RESTful standards and authentication.
4 | API Schema Definition | Infoverity | Signet IT | Accenture | N/A | API schema jointly designed; Infoverity owns schema definition, Accenture consulted.
5 | Connection to Signet Systems | Signet IT | Signet IT | Infoverity, Accenture | Profound Analytics | Integration with Signet systems for triggering product description regeneration events.
6 | E2E (overall) infrastructure design | Signet IT | Accenture | Infoverity | Profound Analytics | providing infrastructure and overall integration design
7 | LLM Visibility Content Strategy | Accenture | Signet IT, Accenture | Profound | Infoverity, Merchandising | LLM visibility content strategy focused on analytics-driven guidance; excludes tone/voice rules.
8 | Analytics Dashboard Setup | Accenture | ecom merch/SEO | Profound | Signet IT | Analytics dashboard setup for monitoring LLM and brand commerce site; includes KPI alignment.
9 | Integration with PIM Workflow | Infoverity | Accenture | Signet IT | Accenture | Integration with PIM workflow via Prodevix; orchestration deprioritized but feedback loops in scope.
10 | Compliance & Human QA | ecom merch/SEO | Brand team (SEO) | Signet IT | Accenture | Mandatory human QA and compliance checks for regenerated content; legal review required.
11 | Update P360 | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
12 | Add new Variant status for AEO Description Requests | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
13 | Update ActiveVOS Workflow | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
14 | Look for products in AEO status | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
15 | Call Prodevix with new AEO flag | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
16 | Update Prodevix (when AEO flag is true) | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
17 | Call AEO Service | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
18 | Use results in description generation | Infoverity | Infoverity | Signet IT, Accenture | ecom merch/SEO | Assumptions: POC only; Production solution requires robust design and error handling.
19 | Profound integration design and build | ESI | Signet IT | Accenture
20 | Infrastructure procurement | Signet IT | Accenture | N/A | N/A | Get infrasturcution provision, ARB, define builiding services, AI committee,JAD
21 | Post go live: define success criteria | ecom merch/SEO | Accenture | Signet IT | Profound Analytics | define success criteria and evaluation post go live
data comes to s3-->push to opensearch
long description is the field that will be used.
inputs for prompt engineer

## Pricing
4-6 weeks
Role | QTY | Location | Level | Duration (Wks) | Responsibilities | Hrs | Price | Total Cost
Technical Analyst | 1 | Onshore | 8 | 3 | 1,2 | 120 | 253 | 30360
AWS API Developer | 1 | Onshore | 8 | 4 | 3,4, 9 | 160 | 253 | 40480
Content Strategist | 1 | Onshore | 9 | 3 | 7 | 120 | 219 | 26280
Profound Reporting Analyst | 1 | Onshore | 8 | 3 | 8 | 120 | 253 | 30360
Delivery Lead | 1 | Onshore | 5 | 5 | Project Plan, Status, 6, 20,21 | 200 | 421 | 84200
QE | 2 | Onshore | 9 | 3 |  | 240 | 202 | 48480
260160
|  |  | Original Proposal |  |  | 375000